## Section A
Criteria: | 20 points
1 | Introduce about the case study (Green Groceries Online Platform: Green Groceries company, business goal)
2 | Introduce about the aim of project? Why do they carry out this project?
3 | Introduce about Development the online platform: Outsourcing, methodologies, framework, dev team, (stakeholders)
4 | Discuss about Agile, why Agile is an appropriate approach? advantages/ disadvantages? What is applied methodology? Why?
5 | What is applied framework? Why? Advantages/ Disadvantages
Example: advantage: - The Agile framework allows for greater flexibility and adaptability in the development process. - Since the company aims to launch its online platform within a relatively short timeframe of three months, Agile methodologies enable iterative development and frequent delivery of working software increments. - This approach allows the company to quickly respond to changes in market demands, user feedback, or business requirements throughout the project, ensuring that the final product aligns closely with customer needs and expectations.
Drawback: - Agile projects rely heavily on collaboration, communication, and decision-making from stakeholders, including product owners and end-users. - If Green Groceries' stakeholders are not fully engaged or available throughout the project, it may lead to delays, misunderstandings, or misalignment between the development team and the business objectives. - Additionally, since the company is outsourcing its software project to System Concepts, ensuring effective communication and collaboration between internal stakeholders and external development teams becomes even more critical.
6 | Conclusion: the approaches are appropriate or not?
Green Groceries Online Platform --> change rapidly, more competitor --> finish project in a short time --> DSDM Atern framework + Scrum --> satisfy condition + advantages

## Section B1.1
Requirements ID: | Requirement Description | Stakeholder | FR/NFR | Reason
GG-2 | Employees would like to have a heathy workspace and 20 office plants | Staff | NFR | It's a nonfunctional requirements (NFR) No related to biz goal No related to the aim of online platform It related to the office management and organization culture
GG-4 | Organize a virtual celebration on the website for the CEO's birthday to showcase the company's fun and friendly culture. | Staff | FR | It should not be used for the CEO's birthday … It should be used for organization culture sharing, and can be in the activities pages. But it did not mention in the aim of the online platform and biz goal. Young biz should focus at the goal short time project --> focus at the aim of project and these pages can be developed in next phases
GG-5 | As the Managing Director I want to be ensured that the site is Data Protection Act safe so that we do not get fined hundreds of thousands of pounds. | Director | NFR | It's a nonfunctional requirements (NFR) It belongs to technical aspect, modern protocols support the encryption already such as HTTPS --> safe while transfering Modern development frameworks support encryption for sensitive information such as bcrypt
GG-7 | As a Customer I want a choice of delivery slots so that I can arrange my diary appropriately. | Customer | FR | Related to a third party for delivery Not in the aim of the project expand the market and accessiblity --> global market --> hard to arrange a fit schedule …
GG-9 | The company should adopt pet-friendly policies to create a positive and inclusive work environment. | Staff | NFR | similar to the GG-2, related to organization policies related to work enviroment not related to the biz goal and the aim of the project
GG-10 | The system must be designed to handle a 30% increase in traffic during peak periods without degradation in performance. | Staff | NFR | It's a nonfunctional requirements (NFR) related to performance design optimization --> improving time by time in the 1st prototype --> not really necessary
GG-15 | All user data, including personal information and payment details, must be encrypted to ensure the highest level of security. | Staff | NFR | It's a nonfunctional requirements (NFR) related to technical aspect modern development frameworks support this encryption
GG-16 | Maintain consistent branding elements and design across the website to reinforce their brand identity. | Staff | NFR | NFR related UI/UX design not clear requirement, no standard for brand identity brand identity will be improved time by time
GG-17 | The development team should participate in a team-building event every quarter to foster collaboration and a positive work environment. | COO | NFR | NFR related to project management no related to biz goal …

## Section B1.2
Requirements ID: | Requirement Description | Stakeholder | FR/NFR | Reason
GG-1 | As an Order Handling Clerk, I want to use the website to process telephone purchases, replacing the paper-based system. | Sale staff | FR | it's quite popular on some e-commerce app Almost people have phone numbers --> useful feature to someone convenience to some old people who are not familiar with the information technologies human communicating GG biz goal: market expand reach and more products accessible
| As a customer, I want to be able to change my account details to ensure my most up-to-date information is recorded. | Users | FR | E-commerce --> must have account profile --> for promotion, payment, delivery , personalization marketing. Personal profile might change overtime For information security and privacy personalization hobby --> improve service quality
| As a customer register an account. | Users | FR | For: creating profile then supoort ordering, payment, delivery, personalization, history of ordering, wishlist… Promotion, personalization marketing financial management
| As a customer, I want to be able to modify my shopping cart | Users | FR | users can change their mind Users can select some products and buy it later users can buy many products at a time …
| As a customer, I want to enter separate delivery and invoice addresses | Users | FR | users might have many addresses, buy products anywhere they want --> in the business goal for delivery buy for someone else Gift …
| As a customer, I want to choose whether or not I am sent marketing information | Users | FR | Legal, spam rules satisfy customer… more effective market …
| As the Marketing Director I would like an offers or discount page so that we can inform our customers of the aforementioned | Marketing Director | FR | Attract more customers Satisfy old customers increase the sold score more competative freeing inventory
| As the Chief Accountant I want to the Web site to adhere to legislation regarding VAT so we are not hit with a hefty fine. | Accountant | FR | Legal, tax not hit with a hefty fine Invoice supplying contribute to government …
| As the Operations Director, I want to accept all forms of payment | CEO | FR | to capture the largest market possible. Market expand and more accessible --> more customers serve to many other countries, over the world or global market more trust in financial ...

## Section B2
Project time: 3 months
SCRUM | 6 sprints, each sprint is 02 weeks
Dev Team
| team members : 5 members ( 4 full-time dev and 1 part-time dev) |  |  |  | from 5-10
Total effort: (4*8 + 1*4 for 1 day)* 5 days per week * 4 weeks per month * 3 months
|  | 2160 | man.hours
| Sprint effort | 360
Estimation for each requirements (WBS - Work breakdown structure)
Num | Requirement ID | Requirement | Break tasks | Estimation (man.hour)
1 | GG-2 | As an Order Handling Clerk, I want to use the website to process telephone purchases, replacing the paper-based system. | 1. Create tables in DB (20 man.hours) 2. Link and create a modal for inputing all info from telephone purchase (50 man.hours) 3. API for submission (100 man.hours) 4. Create route and method for data processing. (30 man.hours) | 200
2 | RQ 2 |  |  | 260
3 | RQ 3 |  |  | 300
4 | RQ 4 |  |  | 400
5 | RQ 5 |  |  | 300
6 | RQ 6 |  |  | 180
7 | RQ 7 |  |  | 150
8 | RQ 8 |  |  | 150
9 | RQ 9 |  |  | 160
Summary |  |  | Total effort | 2100
Prioritize
Requirement ID | Requirement | MoSCoW | Reason for prioritization | Effort | SUMMARY (man.hour) | Scale
RQ1 | As an Order Handling Clerk, I want to use the website to process telephone purchases, replacing the paper-based system. (RQ-1) | Must have | The old system has a telephone based ordering --> inherit for merging this kind of sale to an ecommerce system, this info must be added to the database --> required for VAT. tax for delivery for promotion, … | 200 | 1100 | 53.92%
RQ 2 |  | Must have |  | 200
RQ 3 |  | Must have |  | 300
RQ 4 |  | Must have |  | 400
RQ 5 |  | Should have |  | 300 | 630 | 30.88%
RQ 6 |  | Should have |  | 180
RQ 7 |  | Should have |  | 150
RQ 8 |  | Could have |  | 150 | 310 | 15.2%
RQ 9 |  | Could have |  | 160
|  |  | total | 2040
https://www.techtarget.com/searchsoftwarequality/definition/MoSCoW-method
MoSCoW rule: 60:20:20
the prioritization satisfy the MoSCoW rule with the scale nearly of Musthave:Should have:Could have ~ 60:20:20.
the project can be finished on time as the estimation plan with the MoSCoW prioritization
Apply SCRUM
Adding every tasks to each sprint
In the order of: Must have --> Should have --> Could have
--> Give out conclusion for the plan

## Sprint and MoSCoW
| 180 man.hours/ week | Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4 |  | Sprint 5 |  | Sprint 6
|  | week 1 | week 2 | week 3 | week 4 | week 5 | week 6 | week 7 | week 8 | week 9 | week 10 | week 11 | week 12
Must have | RQ-1 | bar: week 1
RQ-2 | bar: week 1 to week 2
RQ-3 | bar: week 2 to week 3
RQ-4 | bar: week 4 to week 6
Should have | RQ-5 | bar: week 6 to week 8
RQ-6
RQ-7
Could have | RQ-8
RQ-9

## Section C
C1. Data Controller
Discuss about data protection (DPA - Data Protection Act)
Data privacy
What is data controller?
Role of Data controller in Green Groceries? What will they do?
what data will be collected
How to storage data
How to process data
how to transfer data
purpose for data usage
C2. LSEPI
Legal
Data privacy
Security and Fraud detection
Compliance with financial regulation
Guideline c clearly, easy accessing
Intellectual property and license
Terms of Service and User Agreements:
Consumer Protection
Social
Impact to all citizen
Accessibility
technical education of consumer
Web app--> collection info --> privacy ,
Security awareness
Transparent and trust
Ethical
Fairness
protect consumer
Protect business data and info
Professional
Compliance with Standards and Regulations
Test for QA
Security and data protection
The BCS code of conduct